Next Steps / Pilot Plan

## What a Pilot Would Require

A 90-day production pilot would target one Cummins plant (e.g., Columbus Engine Plant) with 15-25 Tier 1 suppliers. The pilot requires: (1) integration with Cummins ERP system (SAP) for live supplier data, parts catalog, and purchase order creation; (2) connection to the existing supplier monitoring feeds for real-time event ingestion; (3) Supabase Postgres instance for persistent audit trail and approval state; (4) SSO integration with Cummins Active Directory for role-based access.

## Minimal Integrations

| Integration | Purpose | Effort | Priority |
| --- | --- | --- | --- |
| SAP ERP (read) | Supplier profiles, parts, AVL data | 2-3 weeks | Critical |
| SAP ERP (write) | Purchase order creation | 2-3 weeks | Critical |
| Supplier monitoring feed | Real-time event ingestion | 1-2 weeks | Critical |
| Cummins SSO (Active Directory) | Role-based authentication | 1 week | High |
| Microsoft Teams | Director notifications and approvals | 1-2 weeks | Medium |
| Supabase Postgres (production) | Persistent data store | 1 week | Critical |

## Effort Estimate

| Phase | Duration | Team Size | Key Activities |
| --- | --- | --- | --- |
| Phase 1: Integration | Weeks 1-4 | 3-4 engineers | SAP connectors, SSO, database migration |
| Phase 2: Validation | Weeks 5-8 | 2-3 engineers + 1 SME | Historical backtesting, threshold tuning, UAT |
| Phase 3: Controlled Rollout | Weeks 9-12 | 2 engineers + 1 ops | Shadow mode, gradual HITL handoff, monitoring |

## Risks

- Data quality: SAP data may have inconsistencies requiring cleansing and mapping to our schema.

- LLM latency: OpenAI API response times may exceed SLA targets during peak usage; mitigated by deterministic fallback engine.

- Change management: Procurement teams may resist AI-driven recommendations; mitigated by HITL design ensuring human control.

- Integration complexity: SAP connector development may take longer than estimated if custom BAPIs are needed.

- Cost overruns: LLM API costs at scale may exceed projections; mitigated by caching and fallback-first strategy.